# Risk Register

Probability and impact are rated Low, Medium, or High, and Priority is derived from the matrix below, adapted from standard project risk management frameworks (Project Management Institute, 2021).

Note: This register is reviewed and updated at every milestone. When a risk

materializes, it becomes an issue and must be linked to the resulting action/

decision.

## Scoring Scale

Probability and impact are rated Low, Medium, or High. Priority is derived from the matrix below.

| Probability/ Impact | Low | Medium | High |
| --- | --- | --- | --- |
| Low | Low | Low | Medium |
| Medium | Low | Medium | High |
| High | Medium | High | Critical |

## Risk register Table

| Risk ID | Description | Cause | Probability | Impact | Priority | Mitigation | Contingency | Owner | Status |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| R-001 | Uncontrolled scope creep after the requirements baseline is signed off. | Pressure to keep adding Requester/Staff/Management capabilities post-baseline; brief allows "additional features" but scope discipline is easy to underestimate. | Medium | High | High | Baseline scope explicitly in PED with in/out/deferred lists; any new capability goes through the Change Management flow before it's built. | Reject or formally defer the change; log it in the Decision Log with rationale instead of silently absorbing it. | Masilo Pudikabekwa | Open |
| R-002 | Misinterpreted or internally conflicting stakeholder needs. | No real client — Requester/Staff/Management needs are simulated by the team, so disagreements on interpretation surface late. | Medium | Medium | Medium | Document stakeholder assumptions explicitly in the Stakeholder Analysis; cross-check derived requirements against all three capability groups before baselining. | Re-run the affected requirement through stakeholder analysis and re-baseline before it propagates further. | Phenyo Phooko | Open |
| R-003 | Team lacks production experience with the technology stack still under evaluation. | Prior team project experience is entirely Node.js/Express/MongoDB; Assignment 1 researched an alternative (Stack B: ASP.NET Core/PostgreSQL) not yet used in a real build. | High | Medium | High | Run a small technical spike/prototype before the M2 architecture decision is finalised; budget extra learning time into the M2 schedule. | Fall back to the stack with existing team experience (Stack A) if the spike shows the learning curve threatens M2 delivery. | Dristen Venter | Open |
| R-004 | Single point of failure per individually owned deliverable. | Exactly 3 team members, each holding fixed individual milestone responsibilities with no formal backup. | Low | High | Medium | Keep all artefacts in the shared repo (not local machines); each member briefly documents their section so another member could pick it up. | Redistribute the affected deliverable across the remaining 2 members and notify the lecturer if the deadline is at risk. | Team (Shared ownership) | Open |
| R-005 | M2 technology decision made without sufficient evidence. | M1 explicitly excludes stack selection; without early spike evidence, the team risks deciding under time pressure at the start of M2. | Medium | Medium | Medium | Start technology comparison research now groundwork already so M2 opens with evidence, not a blank slate | Use a lightweight decision matrix against already-baselined NFRs to force an evidence-based choice quickly | Dristen Venter | Open |
| R-006 | Inconsistent handling of sensitive service-request data (PII, security concerns, location info) | Business need explicitly flags inconsistent handling in the current fragmented process; no authentication/authorisation model exists until M2 | Medium | High | High | Capture data-sensitivity and access control NFRs now, even though implementation is deferred; flag security as a Forward Engineering Consideration | Restrict any early prototype/demo data to synthetic, non-sensitive examples only | Masilo Pudikabekwa | Open |
| R-007 | Secrets or credentials committed to repository history | No secret scanning currently enabled on the repo; a pre-existing committed-secret risk was already flagged during GitHub governance setup | Low | High | Medium | Keep .gitignore current for all credential-bearing file types; treat any committed secret as an immediate history-rewrite trigger, not a routine fix, aligning with industry secrets management standards (OWASP Foundation, n.d.) | Rotate the exposed credential immediately, then rewrite history to remove it before continuing other work | Masilo Pudikabekwa | Open |
| R-008 | Future dependency on a third-party notification channel (e.g. email/SMS) | Current process spans email, phone and WhatsApp; any future integration decision introduces an external API dependency not yet scoped in M1 | Low | Low | Low | Explicitly defer notification-channel integration to a later milestone; record it in Forward Engineering Considerations rather than deciding now | If required earlier than planned, scope it as a small, isolated feature with its own risk/requirement entries first | Phenyo Phooko | Open |
| R-009 | Late discovery of hosting/deployment constraints | CI pipeline and deployment are explicitly out of M1 scope; deferring all environment discussion risks a late surprise in M3/M4 | Medium | Medium | Medium | Note deployment/hosting as a Forward Engineering Consideration now so it isn't a blind spot; revisit before M3 | Use a free-tier hosting option as a fallback to keep M3/M4 delivery on track while cost options are finalised | Dristen Venter | Open |
| R-010 | Operational cost underestimated beyond free tier limits | Constraint requires preferring free/low-cost services, but real hosting/DB cost at scale isn't estimated yet | Medium | Low | Low | Track free tier limits of any service selected in M2 and note them in the relevant ADR | Downgrade to a lower cost equivalent service if a limit is hit during development | Dristen Venter | Open |
| R-011 | Compressed individual working windows against fixed milestone dates | Module runs 31 Aug – 23 Oct 2026 with no schedule flexibility; each member's availability is different and can vary because of other responsibilities. | High | Medium | High | Spread work evenly across the milestone rather than backloading; agree realistic weekly checkpoints in the Team Working Agreement. | Reprioritise remaining scope toward the highest-mark-value items if a member falls behind, and flag it to the team early. | Team (Shared ownership) | Open |
| R-012 | Unsupported or immeasurable quality/NFR claims at the M1 defence | NFRs aren't fully measurable yet at this stage of baseline, and the brief explicitly penalises unsupported quality claims — this affects Requirements & Acceptance Criteria, PED Quality, and the individual defence simultaneously. | High | High | Critical | Attach a measurable acceptance criterion to every NFR before baseline sign-off; reject any NFR that can't be tested or observed. | Mark the NFR as "draft pending measurable criterion" rather than baselining it, and revisit before the sign off. | Phenyo Phooko | Open |
| R-013 | Two-approval PR bottleneck | Protected-main requires 2 approvals excluding the author, from a 3-person team; one unavailable reviewer stalls every merge | Medium | Medium | Medium | Agree a review-turnaround expectation in the Team Working Agreement (e.g. within 24h on weekdays); avoid opening large PRs late in the week | Author pings the team directly / lecturer if a PR is genuinely blocked past the agreed window, rather than bypassing protection | Masilo Pudikabekwa | Open |
| R-014 | Unverified AI-generated content submitted as own work | AI is used throughout the project; the brief states "AI generated it" is never an acceptable defence, and unverified claims risk an integrity penalty | Medium | High | High | Log every material AI contribution in the AI Usage Register with what was verified, changed or rejected, at the time it's used not retroactively | If an unverified AI claim is caught before submission, verify it properly or remove it and redo the work manually | Masilo Pudikabekwa | Open |

### Highest Priority Risk

- R-012: Unsupported or immeasurable quality/NFR claims at the M1 defence

This is the only critical entry because it is one the one risk that that impacts 3 separate rubric lines simultaneously (Requirements and Acceptance Criteria, PED Quality, and the individual engineering defence). It is also actively live; every Non-Functional Requirement (NFR) baselined without a measurable acceptance criterion carries this risk forward. It is fully within the team's control to close before sign-off, which is why the mitigation is to "reject the NFR and do not baseline it" rather than a softer control.